## WBS Diagram
WORK BREAKDOWN STRUCTURE
PROJECT TITLE | Comparing Machine Learning Algorithms for stock prediction and stock index movement using trend deterministic data preparation techniques. |  | GROUP NUMBER | 4
PROJECT MENTOR | Mr. Munish Khanna |  | GROUP MEMBERS | Mohak Kulshrestha, Samar Srivastava, Kashvi Agarwal, Saurabh Arya
PROJECT |  |  | Comparing Machine Learning Algorithms for stock prediction and stock index movement using trend deterministic data preparation techniques.
PHASE Introduction | Paperwork | Planning | Collecting Data Sets | Creating Prediction Models | Evaluating Results
PHASE 2 – Completed on 28th October 2018 | Submit summary of Research papers | Feasibility Study | Downloading datasets of GOOGLE, AMAZON, and APPLE | Implementing Naive Bayes | Score : 85.63%
| Submit Synopsis | Defining Technology Stack | Cleaning GOOGLE Dataset | Implementing Random Forest | Score : 85.63% and F1 score: 88
PHASE 2 – Partially completed, Due to be completed on 1 January 2019
|  | Defining Individual work | Cleaning AMAZON Dataset | Implementing SVM
PHASE 3 – Paritally completed, Due to be completed on 1 January 2019 |  |  | Cleaning APPLE Dataset | Implementing ANN
|  |  | Collecting Stock Indices of GSPC, NDS, and DJI | Implementing XGBoost
PHASE 4 – Partially completed, Due to be completed on 25th March 2019
Implementing LSTMN
| Other Task | Other Task | Collecting GSPC Indices | Other Task